## Sheet1
Author | Douglas Bahr
Date | 2016-11-11
Project | DDS Tone shield
Bring Up Change List
Version | Engineer | Issue | Resolution | Documentation Updated | Time to Complete
REV 1 | Douglas Bahr | POT 5k pads are off | Repad Pot and replace it on board | Arduino DDS shield Rev 6.PcbDoc
REV 1 | Douglas Bahr | POT 100k Pads are off | Repad Pot and replace it on board | Arduino DDS shield Rev 6.PcbDoc
REV 1 | Douglas Bahr | DIP SWITCH pad package is wrong | Figure out where the issue cropped up to note how to avoid it in the future before changing the package size and replaceing the part | DIP switch 8position.lib
REV 1 | Douglas Bahr | Change placement of Via under ON/ON Switch to not be under switch to stop issue of placement of part | Rewire the via | Arduino DDS shield Rev 6.PcbDoc
REV 1 | Douglas Bahr | Anular ring size is too small on all pads /vias | Altium resize the pads/vias | Arduino DDS shield Rev 6.PcbDoc
REV 1 | Douglas Bahr | VIA drill size not complient with 22 guage wire | Change Sizes in altium | Arduino DDS shield Rev 6.PcbDoc
REV 1 | Douglas Bahr | DDS Filter design layout is messy | Replace pads and retrace the lines | Arduino DDS shield Rev 6.PcbDoc
REV 1 | Douglas Bahr | DDS filter change pad/part sizes for easier reworking | Replace pads or modify pads after placement | Arduino DDS shield Rev 6.PcbDoc
REV 1 | Douglas Bahr | Board outline trace exists | Figure out problem and remove it | Arduino DDS shield Rev 6.PcbDoc
REV 1 | Douglas Bahr | Resister/led is in wrong order | Switch in sketch then replace in document | Arduino DDS Shield Rev 6.SchDoc
REV 1 | Douglas Bahr | Sketch is wrong with connection to VCC POT 100k | Change part library and update schematic | Arduino DDS Shield Rev 6.SchDoc
REV 1 | Douglas Bahr | Layout is wrong with connection to VCC POT 100k | Replace and retrace part in layout | Arduino DDS shield Rev 6.PcbDoc
REV 1 | Douglas Bahr | No test points/hard to debug | Add test points and other connections directly to board layout | Arduino DDS shield Rev 6.PcbDoc
REV 1 | Douglas Bahr | Change Solder Mount components to bottom layer | Move each solder mount component to bottom layer | Arduino DDS shield Rev 6.PcbDoc | 4:24 | Hours
REV 2 | Douglas Bahr | Change Board outline for attiny85 input pin to pin 7 (rx pin on attiny)
REV 2 | Douglas Bahr | Change the 3&2 header placement on the board outline and retrace board
REV 2 | Douglas Bahr | Change the pad libarary of the 8 DIP switch so signals coming in connect across to the pads going out
REV 2 | Douglas Bahr | Change Chebyshev filter values to coincide with Product def
REV 2 | Douglas Bahr | Add in Audio Amp for small signal output
REV 2 | Douglas Bahr | Source better 100k POT that has a plunger
REV 2 | Douglas Bahr | Change placement of 5k POT due to placement conflicts
REV 2 | Douglas Bahr | Create hole for speaker housing and source glue to keep speaker in place
REV 2 | Douglas Bahr | Add programming header into board for easier prototyping
REV 2 | Douglas Bahr | Make sure all ground planes are connected and not isolated
REV 2 | Douglas Bahr | Add blocking capacitor to remove DC signal offset post Filter
REV 2 | Douglas Bahr | Product definition rework to coincide with design [LED is controlled by microcontroller and not just the state switch]
REV 2 | Douglas Bahr | Bring up code to accurately have a frequency equal 1-1 to output frequency
REV 2 | Douglas Bahr | Code currently cuts off at around 5kHz